## Budget Detail
HARTWELL CONSTRUCTION GROUP
Riverside Transit Center, Project 24-118
Budget Detail, Period Ending 07/31/2026
PHASE | ITEM NO. | DESCRIPTION OF WORK | COST TYPE | SCHEDULED VALUE | WORK COMPLETED |  | MATERIALS PRESENTLY STORED | BALANCE TO FINISH
[5 empty] | FROM PREVIOUS APPLICATION | THIS PERIOD
Enabling Works | 2026-02-20 | Hazardous Material Survey | O | $248,478.66 | $122,957.44 | $27,172.23 |  | $98,348.99
| 02-220 | Site Demolition | Prof Services | $30,250.00 | $16,740.55 | $4,493.96 |  | $9,015.49
| 02-220 | Site Demolition | M | $105,241.85 | $21,581.12 | $23,871.00 |  | $59,789.73
| 02-230 | Site Clearing | L | $107,031.81 | $31,778.76 | $4,537.25 |  | $70,715.80
| 2026-02-20 | Hazardous Material Survey | LAB | $89,209.76 | $2,151.61 | $23,104.98 |  | $63,953.17
| 01-500 | Temporary Facilities and Controls | Labor | $349,912.69 | $124,913.75 | $49,872.58 | $8,451.69 | $166,674.67
| 01-740 | Cleaning | Labor | $426,651.10 | $237,358.13 | $17,580.14 | $10,223.30 | $161,489.53
| 01-500 | Temporary Facilities and Controls | E | $274,566.33 | $27,054.26 | $39,112.50 |  | $208,399.57
| 02-20 | Hazardous Material Survey | Material | $48,277.65 | $7,546.34 | $9,196.80 |  | $31,534.51
| 02-480 | Dewatering | M | $139,812.06 | $65,501.78 | $8,690.74 |  | $65,619.54
| 02-480 | Dewatering | Equipment | $306,918.90 | $65,840.91 | $19,936.88 |  | $221,141.11
| 01-500 | Temporary Facilities and Controls | Material | $188,633.91 | $90,437.81 | $11,212.22 |  | $86,983.88
| 02-480 | Dewatering | O | $24,451.23 | $17,787.31 | $727.61 |  | $5,936.31
| 02-230 | Site Clearing | M | $126,077.41 | $56,656.27 | $7,881.85 |  | $61,539.29
| 01-740 | Cleaning | Subcontractor | $415,677.44 | $103,479.57 | $4,448.15 |  | $307,749.72
| 2026-02-20 | Hazardous Material Survey | Prof Services | $234,325.41 | $133,040.43 | $6,805.63 |  | $94,479.35
| 02-480 | Dewatering | M | $91,203.08 | $6,625.99 | $18,163.49 |  | $66,413.60
| 02-220 | Site Demolition | Prof Services | $413,539.62 | $120,651.19 | $24,816.97 | $14,204.28 | $253,867.18
| 01-740 | Cleaning | L | $392,643.94 | $195,578.13 | $51,561.19 |  | $145,504.62
| 01-010 | Project Manager | Equipment | $410,675.12 | $261,094.61 | $54,693.48 |  | $94,887.03
| 01-500 | Temporary Facilities and Controls | E | $316,378.01 | $63,980.13 | $93,519.06 |  | $158,878.82
| 01-010 | Project Manager | Labor | $6,480.65 | $3,135.64 | $126.83 |  | $3,218.18
| 2026-02-20 | Hazardous Material Survey | Material | $282,372.20 | $166,145.99 | $32,827.70 |  | $83,398.51
| 01-010 | Project Manager | M | $319,723.95 | $66,979.65 | $18,997.95 |  | $233,746.35
| 02-230 | Site Clearing | Subcontract | $122,245.35 | $23,919.08 | $33,840.59 |  | $64,485.68
| 01-010 | Project Manager | Equipment | $201,381.67 | $121,388.57 | $22,751.41 | $36,593.23 | $20,648.46
| 02-315 | Excavation and Backfill | S | $48,967.63 | $24,954.43 | $6,421.78 |  | $17,591.42
| 01-740 | Cleaning | E | $204,305.24 | $95,036.18 | $30,471.57 |  | $78,797.49
| 02-480 | Dewatering | Subcontractor | $234,199.57 | $150,993.22 | $27,880.13 |  | $55,326.22
| 2026-02-20 | Hazardous Material Survey | M | $81,650.31 | $41,117.48 | $15,915.07 | $4,660.19 | $19,957.57
| 01-740 | Cleaning | Material | $460,878.17 | $137,122.72 | $17,478.65 |  | $306,276.80
| 02-220 | Site Demolition | L | $391,443.43 | $75,437.61 | $115,316.94 |  | $200,688.88
| 02-480 | Dewatering | E | $180,285.98 | $42,581.04 | $26,637.53 | $17,712.91 | $93,354.50
| 02-480 | Dewatering | Owner | $301,329.57 | $90,754.19 | $68,849.33 |  | $141,726.05
| 02-230 | Site Clearing | L | $245,468.78 | $101,387.39 | $57,099.82 |  | $86,981.57
| 2026-02-20 | Hazardous Material Survey | Subcontract | $18,345.96 | $13,260.86 | $123.73 |  | $4,961.37
| 01-500 | Temporary Facilities and Controls | Subcontract | $177,490.86 | $102,236.75 | $8,955.83 |  | $66,298.28
| 02-230 | Site Clearing | S | $140,376.30 | $17,435.30 | $12,524.50 |  | $110,416.50
| 02-480 | Dewatering | L | $333,125.77 | $93,522.72 | $61,352.01 |  | $178,251.04
| 01-010 | Project Manager | E | $8,746.08 | $2,926.45 | $1,907.92 |  | $3,911.71
| 31 23 00 | Excavation and Backfill |  | $72,242.65 | $3,915.41 | $15,862.63 | $22,658.15 | $29,806.46
| 01-500 | Temporary Facilities and Controls | Prof Services | $374,901.70 | $277,218.85 | $33,071.05 |  | $64,611.80
| 31 23 00 | Excavation and Backfill | E | $290,233.68 | $139,358.22 | $25,516.73 |  | $125,358.73
| 02-230 | Site Clearing | E | $139,723.05 | $63,963.54 | $22,752.46 |  | $53,007.05
| 01-740 | Cleaning | E | $446,891.79 | $83,446.85 | $77,522.92 |  | $285,922.02
| 02-480 | Dewatering | Material | $379,803.96 | $51,554.56 | $73,400.34 |  | $254,849.06
| 01-010 | Project Manager | S | $227,275.11 | $55,507.09 | $66,737.03 | $23,654.40 | $81,376.59
| 01-740 | Cleaning | Material | $172,880.43 | $87,852.07 | $9,398.84 | $31,573.71 | $44,055.81
| 02-480 | Dewatering | Sub | $287,766.43 | $72,040.66 | $83,352.27 |  | $132,373.50
| 02.230 | Site Clearing | MAT | $466,024.72 | $237,826.15 | $41,763.04 |  | $186,435.53
| 2026-02-20 | Hazardous Material Survey | M | $72,667.33 | $32,773.08 | $4,859.90 |  | $35,034.35
| 01-740 | Cleaning | M | $100,319.83 | $4,968.67 | $28,431.19 |  | $66,919.97
| 02-315 | Excavation and Backfill |  | $350,734.92 | $122,119.40 | $16,547.68 |  | $212,067.84
| 01-740 | Cleaning |  | $286,099.22 | $179,612.61 | $37,696.13 |  | $68,790.48
| 02-230 | Site Clearing | L | $360,411.88 | $9,823.47 | $72,838.07 |  | $277,750.34
| 02-220 | Site Demolition | MAT | $478,250.10 | $154,747.03 | $19,019.40 |  | $304,483.67
| 01-010 | Project Manager | Subcontractor | $423,737.66 | $106,560.37 | $60,570.88 |  | $256,606.41
| 02-480 | Dewatering | M | $174,624.12 | $70,731.81 | $6,431.44 |  | $97,460.87
| 02-230 | Site Clearing | M | $224,803.49 | $10,370.92 | $84,682.35 |  | $129,750.22
| 02-480 | Dewatering | M | $198,505.13 | $134,251.96 | $12,735.04 |  | $51,518.13
| 2026-02-20 | Hazardous Material Survey | Subcontract | $440,394.59 | $276,232.96 | $33,468.11 |  | $130,693.52
| 2026-02-20 | Hazardous Material Survey | S | $179,448.39 | $111,398.74 | $12,301.76 |  | $55,747.89
| 2026-02-20 | Hazardous Material Survey | Subcontract | $414,899.15 | $69,741.49 | $34,896.86 | $21,801.88 | $288,458.92
| 02-20 | Hazardous Material Survey | L | $144,436.24 | $48,053.54 | $17,542.06 |  | $78,840.64
|  | Enabling Works Total |  | $15,205,849.02
Substructure | 03-210 | Cast-In-Place Concrete | L | $472,468.91 | $174,544.27 | $20,253.81 |  | $277,670.83
| 02-360 | Piling | S | $92,467.96 | $20,141.57 | $14,840.76 |  | $57,485.63
| 03-410 | Precast Concrete Panels | M | $23,740.00 | $7,442.03 | $1,735.70 |  | $14,562.27
| 03 40 00 | Precast Concrete Panels | Material | $377,658.19 | $190,694.65 | $42,419.43 |  | $144,544.11
| 03-300 | Footings | Sub | $176,510.84 | $28,488.37 | $9,846.65 |  | $138,175.82
| 03.210 | Cast-In-Place Concrete | Subcontractor | $356,070.49 | $177,979.06 | $26,764.81 |  | $151,326.62
| 03-210 | Cast-In-Place Concrete | Subcontractor | $438,082.77 | $49,413.03 | $140,241.86 |  | $248,427.88
| 03 30 00 | Cast-In-Place Concrete | S | $210,448.29 | $48,083.22 | $62,355.54 |  | $100,009.53
| 03-410 | Precast Concrete Panels | O | $351,211.91 | $236,399.17 | $24,034.29 |  | $90,778.45
| 03 30 00 | Cast-In-Place Concrete | Labor | $60,121.25 | $209.76 | $7,602.13 |  | $52,309.36
| 07-130 | Waterproofing Below Grade | Labor | $35,927.30 | $27,728.79 | $1,781.97 |  | $6,416.54
| 03-320 | Slab on Grade | Sub | $129,641.13 | $50,499.35 | $7,991.37 | $38,338.02 | $32,812.39
| 03-300 | Footings | S | $194,248.64 | $137,864.21 | $20,120.94 |  | $36,263.49
| 02-360 | Piling | E | $219,650.31 | $157,498.85 | $6,929.94 |  | $55,221.52
| 03-410 | Precast Concrete Panels | LAB | $109,302.26 | $51,300.18 | $3,294.50 |  | $54,707.58
| 03 20 00 | Concrete Reinforcement | M | $30,279.12 | $6,881.08 | $4,150.43 |  | $19,247.61
| 03-100 | Concrete Reinforcement | Subcontract | $360,326.91 | $80,943.96 | $80,421.99 |  | $198,960.96
| 03 20 00 | Concrete Reinforcement | M | $382,579.41 | $145,424.64 | $81,688.94 |  | $155,465.83
| 03-300 | Footings | Subcontract | $127,940.42 | $18,372.88 | $9,647.32 |  | $99,920.22
| 03-300 | Footings | M | $26,709.66 | $5,780.72 | $3,465.10 |  | $17,463.84
| 07-130 | Waterproofing Below Grade | LAB | $42,204.50 | $27,291.54 | $3,587.24 |  | $11,325.72
| 07-130 | Waterproofing Below Grade | M | $483,454.50 | $276,747.08 | $19,977.74 | $17,980.56 | $168,749.12
| 03 40 00 | Precast Concrete Panels | M | $227,081.82 | $19,641.84 | $46,427.28 |  | $161,012.70
| 03.210 | Cast-In-Place Concrete | L | $217,966.01 | $166,323.95 | $4,792.88 | $37,523.60 | $9,325.58
| 03-410 | Precast Concrete Panels | Subcontractor | $377,779.15 | $254,290.57 | $26,061.34 |  | $97,427.24
| 02-360 | Piling | L | $60,334.63 | $29,174.28 | $3,361.69 |  | $27,798.66
| 02-360 | Piling | MAT | $472,676.18 | $153,002.10 | $87,328.90 |  | $232,345.18
| 03.210 | Cast-In-Place Concrete | S | $348,108.27 | $212,130.45 | $35,393.16 | $16,562.69 | $84,021.97
| 03 40 00 | Precast Concrete Panels | E | $94,197.61 | $35,888.22 | $12,338.72 | $28,491.37 | $17,479.30
| 03-410 | Precast Concrete Panels | Subcontractor | $263,716.03 | $70,666.15 | $53,711.50 |  | $139,338.38
| 03-410 | Precast Concrete Panels | E | $409,924.72 | $222,021.21 | $18,880.55 | $6,280.38 | $162,742.58
| 03-300 | Footings | S | $464,031.92 | $84,087.05 | $41,363.30 | $10,198.91 | $328,382.66
| 03 40 00 | Precast Concrete Panels | Equipment | $315,914.38 | $127,260.83 | $35,773.65 |  | $152,879.90
| 03.100 | Concrete Reinforcement | Sub | $303,477.87 | $218,100.72 | $12,664.38 |  | $72,712.77
| 07-130 | Waterproofing Below Grade | M | $91,203.40 | $27,622.75 | $23,223.11 |  | $40,357.54
| 03-410 | Precast Concrete Panels | S | $281,523.09 | $143,736.05 | $33,909.30 |  | $103,877.74
| 07-130 | Waterproofing Below Grade | Material | $208,004.94 | $12,889.24 | $42,903.42 |  | $152,212.28
| 03-300 | Footings | M | $182,187.04 | $51,849.61 | $19,666.52 | $36,721.67 | $73,949.24
| 07-130 | Waterproofing Below Grade | S | $411,462.09 | $319,835.14 | $12,244.16 | $13,017.53 | $66,365.26
| 07-130 | Waterproofing Below Grade | Prof Services | $187,540.54 | $87,079.34 | $12,256.50 |  | $88,204.70
| 03 30 00 | Cast-In-Place Concrete | E | $302,938.73 | $157,559.90 | $47,625.90 |  | $97,752.93
| 03-300 | Footings | L | $12,386.87 | $5,297.81 | $123.36 |  | $6,965.70
| 07-130 | Waterproofing Below Grade | E | $376,491.75 | $127,141.30 | $65,922.32 |  | $183,428.13
| 03-210 | Cast-In-Place Concrete | E | $327,181.56 | $161,507.24 | $45,519.59 |  | $120,154.73
| 03-300 | Footings | M | $222,611.87 | $131,249.71 | $8,475.79 |  | $82,886.37
| 03-300 | Footings | L | $427,170.78 | $60,819.98 | $86,450.95 | $25,819.52 | $254,080.33
| 07-130 | Waterproofing Below Grade | S | $240,646.87 | $33,071.18 | $57,709.64 |  | $149,866.05
| 03-320 | Slab on Grade | Sub | $257,448.54 | $112,139.58 | $12,959.38 |  | $132,349.58
| 03 30 00 | Cast-In-Place Concrete | LAB | $337,603.08 | $90,326.99 | $46,024.07 |  | $201,252.02
| 03.300 | Footings | Equipment | $75,992.77 | $4,346.19 | $28,081.37 |  | $43,565.21
| 03-300 | Footings | S | $373,856.24 | $148,870.80 | $16,869.91 |  | $208,115.53
| 03-300 | Footings | L | $24,842.91 | $6,485.18 | $5,657.41 |  | $12,700.32
| 03 40 00 | Precast Concrete Panels | L | $8,498.53 | $3,625.05 | $1,443.77 |  | $3,429.71
| 03-320 | Slab on Grade | Material | $83,508.52 | $52,802.82 | $5,446.27 |  | $25,259.43
| 03 40 00 | Precast Concrete Panels | S | $141,439.09 | $102,541.74 | $13,722.02 |  | $25,175.33
| 03.100 | Concrete Reinforcement | Equipment | $52,612.04 | $25,864.35 | $1,930.57 |  | $24,817.12
| 03 20 00 | Concrete Reinforcement | M | $450,542.63 | $23,626.32 | $56,661.92 |  | $370,254.39
| 03 30 00 | Cast-In-Place Concrete | E | $142,740.09 | $12,606.33 | $14,855.07 |  | $115,278.69
| 03-210 | Cast-In-Place Concrete | Prof Services | $147,224.84 | $1,579.77 | $134.59 |  | $145,510.48
| 03-410 | Precast Concrete Panels | MAT | $61,635.45 | $36,280.15 | $6,016.93 |  | $19,338.37
| 03-410 | Precast Concrete Panels | Sub | $393,064.29 | $197,816.99 | $42,021.39 |  | $153,225.91
| 03-320 | Slab on Grade | Labor | $105,159.16 | $59,594.24 | $16,000.91 |  | $29,564.01
| 02-360 | Piling | L | $136,400.36 | $16,325.25 | $42,186.81 |  | $77,888.30
| 03 20 00 | Concrete Reinforcement | S | $129,882.90 | $100,788.58 | $5,217.45 | $18,261.96 | $5,614.91
| 03 40 00 | Precast Concrete Panels | L | $444,375.51 | $264,835.66 | $33,819.34 |  | $145,720.51
| 03-320 | Slab on Grade | LAB | $255,749.32 | $77,764.32 | $47,677.36 |  | $130,307.64
| 03 40 00 | Precast Concrete Panels | L | $63,958.69 | $48,404.14 | $5,937.44 |  | $9,617.11
| 03-300 | Footings | E | $76,421.80 | $27,554.15 | $17,256.85 |  | $31,610.80
| 03-300 | Footings | M | $399,752.27 | $271,385.18 | $33,467.22 |  | $94,899.87
| 03-300 | Footings | Sub | $300,326.76 | $228,243.21 | $24,605.56 |  | $47,477.99
| 02-360 | Piling | Labor | $366,916.02 | $44,675.24 | $125,627.25 |  | $196,613.53
| 02-360 | Piling | E | $161,987.71 | $99,628.28 | $14,627.93 |  | $47,731.50
| 03-300 | Footings | Subcontract | $183,182.75 | $136,818.18 | $13,744.18 |  | $32,620.39
| 07-130 | Waterproofing Below Grade | LAB | $237,404.41 | $158,113.29 | $10,072.51 | $18,466.52 | $50,752.09
| 07-130 | Waterproofing Below Grade | Material | $8,455.24 | $1,751.26 | $2,515.64 |  | $4,188.34
| 03-320 | Slab on Grade | Subcontract | $64,092.03 | $10,435.33 | $14,737.77 |  | $38,918.93
| 03-210 | Cast-In-Place Concrete | Material | $98,085.48 | $66,814.61 | $2,977.58 |  | $28,293.29
| 03 30 00 | Cast-In-Place Concrete | Sub | $374,067.71 | $59,149.76 | $88,462.95 |  | $226,455.00
| 03-100 | Concrete Reinforcement | Subcontract | $474,444.50 | $331,003.40 | $9,397.32 |  | $134,043.78
| 03-410 | Precast Concrete Panels | O | $108,211.46 | $25,808.12 | $27,560.90 |  | $54,842.44
| 03-100 | Concrete Reinforcement | Material | $315,901.02 | $193,224.78 | $20,537.22 |  | $102,139.02
| 03-100 | Concrete Reinforcement | Subcontract | $74,528.33 | $32,897.54 | $15,024.25 |  | $26,606.54
| 03-100 | Concrete Reinforcement | L | $175,596.28 | $118,522.24 | $10,662.09 |  | $46,411.95
| 07-130 | Waterproofing Below Grade | Labor | $71,741.31 | $3,524.31 | $24,168.21 |  | $44,048.79
| 03-100 | Concrete Reinforcement | S | $61,163.44 | $18,822.35 | $8,140.13 |  | $34,200.96
| 03 20 00 | Concrete Reinforcement | Material | $429,024.20 | $210,725.65 | $25,575.92 | $35,076.42 | $157,646.21
| 03-320 | Slab on Grade | LAB | $139,684.12 | $49,827.54 | $20,622.10 | $25,562.37 | $43,672.11
| 03-320 | Slab on Grade | L | $273,286.24 | $171,811.61 | $37,015.65 |  | $64,458.98
|  | Substructure Total |  | $19,608,410.93
Superstructure | 03-100 | Concrete Reinforcement | Material | $69,213.36 | $14,692.52 | $11,710.20 |  | $42,810.64
| 03 30 00 | Cast-In-Place Concrete | Material | $482,701.43 | $184,799.42 | $42,078.52 |  | $255,823.49
| 05-310 | Steel Deck | S | $273,900.75 | $141,685.95 | $12,137.84 |  | $120,076.96
| 06-100 | Rough Carpentry | L | $478,479.45 | $177,603.13 | $77,760.56 |  | $223,115.76
| 05-120 | Structural Steel Framing | S | $401,708.31 | $62,673.69 | $47,849.58 |  | $291,185.04
| 05-120 | Structural Steel Framing | L | $354,075.62 | $201,574.08 | $10,120.42 |  | $142,381.12
| 03 20 00 | Concrete Reinforcement | E | $225,309.39 | $17,002.52 | $77,818.56 |  | $130,488.31
| 06-100 | Rough Carpentry | S | $167,968.34 | $18,421.33 | $38,372.42 |  | $111,174.59
| 2026-05-12 | Steel Erection | E | $140,563.74 | $55,809.51 | $32,630.15 |  | $52,124.08
| 2026-05-12 | Steel Erection | L | $261,157.92 | $185,170.46 | $7,374.77 |  | $68,612.69
| 05-120 | Structural Steel Framing | LAB | $362,168.16 | $62,856.94 | $59,447.20 |  | $239,864.02
| 03 30 00 | Cast-In-Place Concrete | L | $368,918.51 | $28,369.90 | $77,620.00 |  | $262,928.61
| 05-310 | Steel Deck | Material | $394,492.83 | $255,807.54 | $14,471.75 |  | $124,213.54
| 05-310 | Steel Deck | Labor | $279,450.75 | $154,096.76 | $43,204.21 |  | $82,149.78
| 05-120 | Structural Steel Framing | L | $160,998.96 | $15,933.24 | $51,215.21 |  | $93,850.51
| 03-450 | Precast Structural Framing | Subcontractor | $121,900.98 | $66,822.49 | $6,328.62 |  | $48,749.87
| 03-100 | Concrete Reinforcement | S | $420,562.06 | $249,443.90 | $40,221.64 |  | $130,896.52
| 03 40 00 | Precast Structural Framing | L | $282,729.39 | $194,232.41 | $13,640.07 | $38,972.66 | $35,884.25
| 05-310 | Steel Deck | S | $291,604.70 | $216,654.29 | $26,702.66 |  | $48,247.75
| 03 20 00 | Concrete Reinforcement | M | $280,086.16 | $7,968.27 | $94,077.61 |  | $178,040.28
| 05-120 | Structural Steel Framing | S | $369,124.24 | $246,333.03 | $8,939.05 |  | $113,852.16
| 2026-05-12 | Steel Erection | M | $384,086.16 | $281,870.60 | $3,859.78 | $14,525.97 | $83,829.81
| 05-120 | Structural Steel Framing | Equipment | $41,652.33 | $28,257.78 | $2,383.82 |  | $11,010.73
| 2026-05-12 | Steel Erection | L | $405,733.15 | $19,683.68 | $145,958.53 |  | $240,090.94
| 05-120 | Structural Steel Framing | L | $211,589.60 | $139,075.00 | $2,540.99 |  | $69,973.61
| 03 40 00 | Precast Structural Framing | Subcontract | $288,507.35 | $177,841.97 | $32,017.02 |  | $78,648.36
| 05-120 | Structural Steel Framing | L | $262,337.20 | $70,545.66 | $67,103.00 |  | $124,688.54
| 03 30 00 | Cast-In-Place Concrete | M | $271,021.29 | $79,639.64 | $19,420.61 |  | $171,961.04
| 03 30 00 | Cast-In-Place Concrete | M | $150,653.54 | $88,269.75 | $22,264.49 | $20,046.65 | $20,072.65
| 05-120 | Structural Steel Framing | Material | $276,253.23 | $66,548.75 | $12,481.03 |  | $197,223.45
| 05-310 | Steel Deck | Subcontract | $102,945.36 | $55,136.93 | $8,631.14 | $11,846.27 | $27,331.02
| 05-120 | Structural Steel Framing | L | $317,901.36 | $210,462.24 | $28,654.15 |  | $78,784.97
| 03-450 | Precast Structural Framing | E | $274,810.08 | $101,615.90 | $46,951.84 |  | $126,242.34
| 05-310 | Steel Deck | L | $127,260.21 | $21,523.70 | $31,424.66 |  | $74,311.85
| 06-100 | Rough Carpentry | E | $122,044.68 | $16,564.65 | $14,189.03 |  | $91,291.00
| 06-100 | Rough Carpentry | L | $385,003.77 | $97,770.45 | $79,436.93 |  | $207,796.39
| 03-210 | Cast-In-Place Concrete | Subcontract | $71,342.92 | $35,232.07 | $5,231.59 |  | $30,879.26
| 03-100 | Concrete Reinforcement | M | $121,988.43 | $54,216.36 | $11,314.74 |  | $56,457.33
| 06-100 | Rough Carpentry | Sub | $49,210.88 | $19,162.86 | $6,794.98 |  | $23,253.04
| 03-210 | Cast-In-Place Concrete | Subcontract | $65,168.77 | $36,135.64 | $9,998.26 |  | $19,034.87
| 03-100 | Concrete Reinforcement | O | $111,373.24 | $46,156.80 | $11,376.50 |  | $53,839.94
| 2026-05-12 | Steel Erection | Subcontractor | $62,310.82 | $19,085.21 | $15,085.02 | $29,954.67 | $-1,814.08
| 06-100 | Rough Carpentry | L | $131,063.72 | $62,749.27 | $4,588.90 |  | $63,725.55
| 2026-05-12 | Steel Erection | Owner | $355,243.03 | $3,228.53 | $39,486.15 |  | $312,528.35
| 05.120 | Structural Steel Framing | Equipment | $224,525.15 | $119,472.86 | $31,198.98 |  | $73,853.31
| 2026-05-12 | Steel Erection | S | $259,645.03 | $161,589.74 | $6,913.99 |  | $91,141.30
| 03-450 | Precast Structural Framing | L | $192,283.84 | $131,398.46 | $14,973.40 |  | $45,911.98
| 03-100 | Concrete Reinforcement | Sub | $34,591.15 | $10,574.59 | $411.44 |  | $23,605.12
| 05-310 | Steel Deck | L | $350,360.81 | $218,790.61 | $35,384.20 |  | $96,186.00
| 2026-05-12 | Steel Erection | M | $13,445.31 | $6,300.57 | $945.05 |  | $6,199.69
| 03 40 00 | Precast Structural Framing | M | $82,711.17 | $56,196.20 | $7,725.78 |  | $18,789.19
| 03 20 00 | Concrete Reinforcement | S | $131,110.83 | $67,274.84 | $13,328.41 |  | $50,507.58
| 05-120 | Structural Steel Framing | L | $463,668.17 | $103,992.56 | $60,244.61 |  | $299,431.00
| 2026-05-12 | Steel Erection | L | $463,760.33 | $330,571.31 | $36,751.63 |  | $96,437.39
| 03-100 | Concrete Reinforcement | Material | $183,409.88 | $70,612.17 | $15,323.48 |  | $97,474.23
| 2026-05-12 | Steel Erection | E | $316,751.06 | $111,093.02 | $684.94 |  | $204,973.10
| 05-120 | Structural Steel Framing | Labor | $466,443.40 | $319,910.31 | $52,495.69 |  | $94,037.40
| 05-310 | Steel Deck | M | $190,320.81 | $5,956.29 | $47,643.82 |  | $136,720.70
| 03-100 | Concrete Reinforcement | Equipment | $197,542.14 | $19,630.41 | $9,553.81 |  | $168,357.92
| 05-310 | Steel Deck | Equipment | $288,202.34 | $6,725.26 | $20,392.29 |  | $261,084.79
| 2026-05-12 | Steel Erection | Sub | $293,733.94 | $154,984.66 | $53,962.02 |  | $84,787.26
| 05-12 | Steel Erection | Equipment | $182,581.25 | $122,710.35 | $5,238.53 |  | $54,632.37
| 03-210 | Cast-In-Place Concrete | L | $297,042.83 | $73,925.40 | $1,706.02 |  | $221,411.41
| 06-100 | Rough Carpentry | Subcontractor | $479,427.44 | $49,247.89 | $32,016.11 | $31,098.44 | $367,065.00
| 05-310 | Steel Deck | Subcontractor | $80,725.42 | $41,334.37 | $9,338.06 |  | $30,052.99
| 03 20 00 | Concrete Reinforcement | M | $301,881.86 | $177,789.61 | $12,552.22 | $15,192.86 | $96,347.17
| 2026-05-12 | Steel Erection | L | $13,337.88 | $5,466.32 | $1,504.51 |  | $6,367.05
| 03 30 00 | Cast-In-Place Concrete | S | $448,596.50 | $50,635.78 | $147,539.56 |  | $250,421.16
| 2026-05-12 | Steel Erection | M | $59,869.44 | $30,465.94 | $6,338.06 | $32,157.79 | $-9,092.35
| 03 30 00 | Cast-In-Place Concrete | Subcontract | $71,199.49 | $35,499.92 | $6,950.61 |  | $28,748.96
| 06-100 | Rough Carpentry | Sub | $176,422.50 | $118,766.41 | $5,990.13 |  | $51,665.96
| 03-210 | Cast-In-Place Concrete | Owner | $222,646.56 | $137,506.98 | $5,472.41 |  | $79,667.17
| 05-120 | Structural Steel Framing | Prof Services | $443,368.74 | $180,419.77 | $38,807.59 |  | $224,141.38
| 05-120 | Structural Steel Framing | Material | $404,499.21 | $271,052.60 | $29,224.20 |  | $104,222.41
| 06-100 | Rough Carpentry | M | $133,408.19 | $10,079.93 | $34,733.85 |  | $88,594.41
| 05-310 | Steel Deck |  | $484,925.52 | $25,079.90 | $153,951.41 |  | $305,894.21
| 03-450 | Precast Structural Framing | Material | $359,716.35 | $208,221.15 | $9,752.71 |  | $141,742.49
| 03-210 | Cast-In-Place Concrete | Subcontract | $237,717.59 | $106,234.99 | $39,609.88 |  | $91,872.72
| 06-100 | Rough Carpentry | E | $38,252.22 | $3,861.61 | $7,422.57 | $26,040.38 | $927.66
| 03-100 | Concrete Reinforcement | Subcontract | $361,178.79 | $28,307.18 | $61,467.53 |  | $271,404.08
| 05-310 | Steel Deck | Material | $236,157.99 | $176,822.06 | $15,706.26 |  | $43,629.67
| 05-120 | Structural Steel Framing | E | $398,206.52 | $51,511.51 | $121,634.30 |  | $225,060.71
| 06-100 | Rough Carpentry | MAT | $373,341.18 | $87,746.21 | $55,856.05 |  | $229,738.92
| 03.450 | Precast Structural Framing | M | $41,002.38 | $9,928.07 | $2,848.36 |  | $28,225.95
| 03 20 00 | Concrete Reinforcement | Labor | $384,733.88 | $176,428.43 | $10,218.69 |  | $198,086.76
| 03-210 | Cast-In-Place Concrete | M | $234,923.66 | $93,208.28 | $18,963.13 | $24,395.47 | $98,356.78
| 03 20 00 | Concrete Reinforcement | S | $57,654.11 | $30,866.54 | $2,505.06 |  | $24,282.51
| 05-120 | Structural Steel Framing | L | $139,896.40 | $37,875.63 | $32,255.29 |  | $69,765.48
| 03-100 | Concrete Reinforcement | L | $154,381.00 | $85,115.09 | $12,417.90 |  | $56,848.01
| 05-12 | Steel Erection | LAB | $433,589.09 | $10,576.69 | $20,146.72 |  | $402,865.68
| 03 20 00 | Concrete Reinforcement | M | $120,307.77 | $69,490.84 | $7,301.96 |  | $43,514.97
| 05-310 | Steel Deck | E | $352,834.99 | $83,285.76 | $81,098.12 |  | $188,451.11
| 06-100 | Rough Carpentry | S | $421,949.07 | $89,123.63 | $114,309.84 |  | $218,515.60
| 05-120 | Structural Steel Framing | MAT | $294,555.92 | $219,765.39 | $12,761.29 |  | $62,029.24
| 03-100 | Concrete Reinforcement | M | $2,686.30 | $64.24 | $609.08 |  | $2,012.98
| 03-210 | Cast-In-Place Concrete | Subcontract | $366,038.81 | $185,378.74 | $19,087.49 | $41,529.77 | $120,042.81
|  | Superstructure Total |  | $23,738,178.38
Envelope | 08.410 | Aluminium Entrances and Storefronts | M | $340,953.53 | $54,787.27 | $34,970.85 |  | $251,195.41
| 08 44 00 | Curtain Wall | M | $275,856.74 | $79,883.90 | $54,375.76 | $35,981.84 | $105,615.24
| 07-540 | Thermoplastic Membrane Roofing | S | $451,339.91 | $14,325.70 | $66,547.36 |  | $370,466.85
| 08-410 | Aluminium Entrances and Storefronts | Labor | $312,986.31 | $118,741.99 | $61,893.53 |  | $132,350.79
| 08-440 | Curtain Wall | Labor | $193,113.08 | $71,996.42 | $6,967.88 |  | $114,148.78
| 04-200 | Unit Masonry | Equipment | $360,861.23 | $11,329.31 | $11,486.26 | $9,590.45 | $328,455.21
| 04-200 | Unit Masonry | S | $343,331.01 | $40,728.43 | $86,250.46 |  | $216,352.12
| 07-410 | Metal Roof Panels | S | $236,466.10 | $114,475.06 | $10,268.53 |  | $111,722.51
| 08-410 | Aluminium Entrances and Storefronts | L | $241,892.57 | $152,155.44 | $5,368.12 |  | $84,369.01
| 07-410 | Metal Roof Panels |  | $383,400.74 | $251,941.55 | $31,819.80 |  | $99,639.39
| 07 21 00 | Thermal Insulation | Labor | $102,395.66 | $15,447.08 | $26,733.67 |  | $60,214.91
| 04.200 | Unit Masonry | MAT | $340,931.69 | $27,967.10 | $101,175.20 |  | $211,789.39
| 07-920 | Joint Sealants | L | $347,900.56 | $31,607.32 | $43,609.97 |  | $272,683.27
| 08-410 | Aluminium Entrances and Storefronts | S | $411,680.02 | $34,289.80 | $85,702.61 |  | $291,687.61
| 07-540 | Thermoplastic Membrane Roofing | MAT | $247,325.97 | $15,935.43 | $56,350.76 |  | $175,039.78
| 08-410 | Aluminium Entrances and Storefronts | Prof Services | $350,990.01 | $120,107.97 | $31,025.95 |  | $199,856.09
| 04-200 | Unit Masonry | L | $163,720.19 | $11,691.84 | $41,992.74 |  | $110,035.61
| 08-410 | Aluminium Entrances and Storefronts | MAT | $89,344.92 | $64,729.38 | $4,365.85 |  | $20,249.69
| 07-210 | Thermal Insulation | M | $293,215.97 | $75,953.86 | $60,228.25 |  | $157,033.86
| 08-410 | Aluminium Entrances and Storefronts | M | $385,185.77 | $278,748.04 | $10,822.93 |  | $95,614.80
| 08 44 00 | Curtain Wall | Equipment | $477,596.75 | $50,787.23 | $156,712.92 |  | $270,096.60
| 08-440 | Curtain Wall | E | $476,358.99 | $98,944.93 | $132,095.02 |  | $245,319.04
| 07-540 | Thermoplastic Membrane Roofing | Material | $100,389.52 | $20,710.83 | $5,436.32 | $31,752.56 | $42,489.81
| 07-410 | Metal Roof Panels | Labor | $304,993.46 | $94,923.65 | $38,848.10 | $16,680.10 | $154,541.61
| 04-200 | Unit Masonry | LAB | $19,285.75 | $209.58 | $5,058.82 | $3,914.20 | $10,103.15
| 07-210 | Thermal Insulation | L | $112,149.84 | $39,012.30 | $15,366.73 |  | $57,770.81
| 08 44 00 | Curtain Wall | Labor | $100,509.33 | $25,476.00 | $8,262.76 |  | $66,770.57
| 07 54 00 | Thermoplastic Membrane Roofing | Prof Services | $317,097.40 | $18,137.35 | $91,758.34 |  | $207,201.71
| 08-440 | Curtain Wall | S | $40,221.85 | $9,705.43 | $5,569.34 |  | $24,947.08
| 07-540 | Thermoplastic Membrane Roofing | S | $372,253.28 | $20,696.84 | $6,978.80 | $9,598.55 | $334,979.09
| 07-920 | Joint Sealants | Equipment | $409,739.69 | $48,794.77 | $121,042.05 |  | $239,902.87
| 07-410 | Metal Roof Panels | M | $156,818.83 | $66,277.50 | $4,147.47 | $24,463.14 | $61,930.72
| 07-210 | Thermal Insulation | Sub | $211,695.03 | $128,993.25 | $13,066.72 |  | $69,635.06
| 08-410 | Aluminium Entrances and Storefronts | Labor | $457,869.74 | $133,095.56 | $72,960.78 |  | $251,813.40
| 07-920 | Joint Sealants | Subcontract | $172,881.98 | $51,571.92 | $7,421.80 |  | $113,888.26
| 07-920 | Joint Sealants | S | $208,353.70 | $58,903.76 | $49,353.01 | $8,984.69 | $91,112.24
| 04 20 00 | Unit Masonry | LAB | $307,213.81 | $141,774.52 | $38,784.71 | $8,976.94 | $117,677.64
| 07-410 | Metal Roof Panels | Labor | $33,129.41 | $22,822.31 | $3,171.16 |  | $7,135.94
| 08 44 00 | Curtain Wall | Material | $446,101.62 | $289,819.79 | $40,051.00 | $25,335.09 | $90,895.74
| 08-410 | Aluminium Entrances and Storefronts | L | $397,021.72 | $180,301.43 | $53,869.06 |  | $162,851.23
| 07 54 00 | Thermoplastic Membrane Roofing |  | $182,363.21 | $83,049.54 | $31,294.63 | $34,680.22 | $33,338.82
| 07 54 00 | Thermoplastic Membrane Roofing | S | $240,478.97 | $76,586.18 | $64,528.16 |  | $99,364.63
| 07-920 | Joint Sealants | Labor | $312,811.04 | $208,451.36 | $23,019.09 |  | $81,340.59
| 07-210 | Thermal Insulation | Prof Services | $315,160.60 | $217,192.76 | $21,320.09 |  | $76,647.75
| 07 21 00 | Thermal Insulation | Material | $33,887.85 | $25,563.48 | $240.16 |  | $8,084.21
| 07-410 | Metal Roof Panels | L | $223,850.63 | $134,489.41 | $15,249.14 |  | $74,112.08
| 07-920 | Joint Sealants | M | $135,131.55 | $56,741.85 | $9,086.14 |  | $69,303.56
| 07-920 | Joint Sealants | E | $304,707.12 | $181,092.17 | $23,713.82 |  | $99,901.13
| 08-440 | Curtain Wall | Material | $139,741.41 | $89,171.01 | $16,902.29 |  | $33,668.11
| 08-440 | Curtain Wall | Labor | $337,287.97 | $13,342.29 | $28,648.83 |  | $295,296.85
| 08 44 00 | Curtain Wall | Equipment | $435,060.17 | $178,240.99 | $35,736.20 |  | $221,082.98
| 04 20 00 | Unit Masonry | O | $395,224.49 | $300,990.19 | $34,476.38 |  | $59,757.92
| 07-920 | Joint Sealants | M | $164,977.14 | $90,171.25 | $29,715.93 |  | $45,089.96
| 07.210 | Thermal Insulation | M | $9,768.87 | $2,741.62 | $2,500.20 |  | $4,527.05
| 07 54 00 | Thermoplastic Membrane Roofing | S | $234,451.21 | $106,138.14 | $22,901.69 |  | $105,411.38
| 08-440 | Curtain Wall | Subcontractor | $53,107.18 | $2,584.97 | $2,412.95 | $34,254.33 | $13,854.93
| 08-440 | Curtain Wall | Subcontractor | $230,353.47 | $34,044.84 | $7,788.93 |  | $188,519.70
| 07-210 | Thermal Insulation | Material | $8,937.09 | $1,908.59 | $1,282.02 |  | $5,746.48
| 08-410 | Aluminium Entrances and Storefronts | Subcontractor | $180,267.38 | $44,668.36 | $43,948.46 |  | $91,650.56
| 08 44 00 | Curtain Wall | M | $413,588.82 | $157,656.66 | $8,541.82 |  | $247,390.34
| 07-410 | Metal Roof Panels | M | $36,950.59 | $17,603.74 | $2,501.49 |  | $16,845.36
| 04 20 00 | Unit Masonry | L | $167,276.13 | $4,582.35 | $27,978.16 |  | $134,715.62
| 07-410 | Metal Roof Panels | S | $164,130.76 | $16,447.42 | $22,218.13 | $35,123.52 | $90,341.69
| 08-410 | Aluminium Entrances and Storefronts | Equipment | $275,053.44 | $85,076.70 | $4,164.99 |  | $185,811.75
| 07-540 | Thermoplastic Membrane Roofing | MAT | $34,518.03 | $20,859.20 | $2,018.61 |  | $11,640.22
| 04-200 | Unit Masonry | Equipment | $278,471.66 | $24,894.95 | $68,815.22 |  | $184,761.49
| 07-540 | Thermoplastic Membrane Roofing | Owner | $113,411.73 | $47,508.18 | $12,335.27 | $24,644.79 | $28,923.49
| 07-410 | Metal Roof Panels | Labor | $402,975.67 | $2,499.01 | $77,914.67 | $5,704.73 | $316,857.26
| 07-920 | Joint Sealants | Labor | $283,932.12 | $65,373.94 | $33,945.17 |  | $184,613.01
| 04-200 | Unit Masonry | L | $85,649.72 | $39,159.66 | $2,338.70 |  | $44,151.36
| 08-440 | Curtain Wall | Sub | $100,710.31 | $38,878.65 | $15,872.34 | $18,719.88 | $27,239.44
| 07-210 | Thermal Insulation | S | $277,253.34 | $179,956.71 | $1,081.55 |  | $96,215.08
| 08 44 00 | Curtain Wall | L | $324,658.42 | $170,649.13 | $53,564.98 |  | $100,444.31
| 07-540 | Thermoplastic Membrane Roofing | S | $94,751.19 | $6,360.79 | $34,688.83 | $22,190.79 | $31,510.78
| 07 21 00 | Thermal Insulation | L | $77,282.34 | $25,811.36 | $18,276.54 | $8,834.01 | $24,360.43
| 07-540 | Thermoplastic Membrane Roofing | M | $438,493.44 | $221,772.71 | $49,257.39 |  | $167,463.34
| 04 20 00 | Unit Masonry | M | $73,612.42 | $57,236.79 | $4,327.50 |  | $12,048.13
| 04-200 | Unit Masonry | L | $8,506.45 | $808.88 | $1,835.24 | $36,451.55 | $-30,589.22
| 07-920 | Joint Sealants | MAT | $77,391.96 | $15,982.65 | $22,553.73 |  | $38,855.58
| 07.210 | Thermal Insulation | LAB | $286,341.46 | $143,517.93 | $49,725.98 |  | $93,097.55
| 07-410 | Metal Roof Panels | Subcontractor | $133,158.60 | $63,548.34 | $5,639.78 |  | $63,970.48
| 07-210 | Thermal Insulation | LAB | $74,324.14 | $11,122.10 | $21,535.99 |  | $41,666.05
|  | Envelope Total |  | $19,154,583.77
Interiors | 09-250 | Gypsum Board Assemblies | Equipment | $220,349.03 | $17,816.70 | $41,495.09 |  | $161,037.24
| 09-650 | Resilient Flooring | Subcontractor | $437,744.05 | $71,964.61 | $46,588.89 |  | $319,190.55
| 09.650 | Resilient Flooring | Labor | $385,261.46 | $48,132.18 | $70,690.02 |  | $266,439.26
| 09-910 | Painting | Prof Services | $237,086.52 | $116.76 | $58,108.91 |  | $178,860.85
| 09-510 | Acoustical Ceilings | Subcontract | $84,736.66 | $47,397.24 | $3,888.29 |  | $33,451.13
| 09-650 | Resilient Flooring | E | $206,227.66 | $83,732.02 | $27,723.48 |  | $94,772.16
| 10-280 | Toilet Accessories | Equipment | $346,164.77 | $107,148.48 | $75,507.76 |  | $163,508.53
| 09-30 | Tiling | O | $250,952.59 | $44,680.86 | $24,397.28 | $21,517.64 | $160,356.81
| 09-510 | Acoustical Ceilings | Subcontractor | $350,190.43 | $24,356.73 | $105,379.93 |  | $220,453.77
| 08-110 | Steel Doors and Frames | Subcontract | $476,727.49 | $152,771.97 | $81,568.79 |  | $242,386.73
| 08-110 | Steel Doors and Frames | Subcontract | $335,206.94 | $176,852.33 | $34,211.80 |  | $124,142.81
| 08-110 | Steel Doors and Frames | S | $369,009.44 | $144,271.14 | $28,959.89 |  | $195,778.41
| 09-650 | Resilient Flooring | L | $13,159.59 | $3,547.32 | $2,935.65 | $26,415.28 | $-19,738.66
| 09.910 | Painting | Material | $22,012.25 | $15,620.46 | $619.86 |  | $5,771.93
| 10-280 | Toilet Accessories | Equipment | $49,426.38 | $14,862.52 | $3,643.29 |  | $30,920.57
| 09 91 00 | Painting | M | $352,742.71 | $142,408.59 | $8,851.18 | $10,972.36 | $190,510.58
| 09 29 00 | Gypsum Board Assemblies | Subcontractor | $182,090.22 | $112,752.22 | $8,263.93 |  | $61,074.07
| 08-110 | Steel Doors and Frames | M | $264,600.17 | $90,600.62 | $45,547.12 |  | $128,452.43
| 09-510 | Acoustical Ceilings | S | $343,144.31 | $76,038.23 | $101,402.59 | $23,993.71 | $141,709.78
| 2026-09-30 | Tiling | M | $307,283.80 | $48,848.99 | $65,186.02 |  | $193,248.79
| 10-280 | Toilet Accessories | Subcontract | $54,610.85 | $5,625.33 | $611.37 |  | $48,374.15
| 09-510 | Acoustical Ceilings | Labor | $346,691.33 | $219,870.58 | $13,789.46 |  | $113,031.29
| 08-110 | Steel Doors and Frames | S | $299,959.64 | $199,342.93 | $36,699.74 | $8,299.44 | $55,617.53
| 10-280 | Toilet Accessories | M | $393,860.22 | $2,557.26 | $99,952.70 |  | $291,350.26
| 10-280 | Toilet Accessories | E | $198,583.21 | $23,231.88 | $2,453.69 |  | $172,897.64
| 12-480 | Entrance Floor Mats | Material | $362,419.84 | $239,534.90 | $18,006.38 |  | $104,878.56
| 12-480 | Entrance Floor Mats | S | $426,627.96 | $128,368.85 | $104,126.72 | $34,525.14 | $159,607.25
| 10-280 | Toilet Accessories | Subcontract | $161,654.65 | $24,790.06 | $45,323.13 |  | $91,541.46
| 08-110 | Steel Doors and Frames | MAT | $200,037.52 | $143,798.93 | $553.69 | $38,503.39 | $17,181.51
| 09-250 | Gypsum Board Assemblies | E | $210,853.71 | $147,969.30 | $9,647.28 | $16,443.87 | $36,793.26
| 09-250 | Gypsum Board Assemblies | E | $385,540.26 | $174,061.68 | $24,227.63 | $22,205.62 | $165,045.33
| 2026-09-30 | Tiling | M | $7,232.13 | $1,015.91 | $1,928.08 |  | $4,288.14
| 09-910 | Painting | E | $211,955.56 | $53,466.21 | $37,946.49 |  | $120,542.86
| 09 91 00 | Painting | O | $387,123.48 | $37.85 | $40,297.90 |  | $346,787.73
| 09-30 | Tiling | Labor | $175,406.27 | $58,744.37 | $38,103.71 | $8,069.38 | $70,488.81
| 08-110 | Steel Doors and Frames | Sub | $245,391.06 | $56,212.05 | $27,964.97 |  | $161,214.04
| 09-650 | Resilient Flooring | L | $461,781.39 | $7,486.43 | $20,560.31 |  | $433,734.65
| 09-250 | Gypsum Board Assemblies | L | $383,689.99 | $6,459.54 | $7,377.89 |  | $369,852.56
| 10-280 | Toilet Accessories | Subcontract | $338,204.60 | $176,383.04 | $17,249.52 |  | $144,572.04
| 10-280 | Toilet Accessories | Labor | $199,649.77 | $127,081.72 | $10,680.36 |  | $61,887.69
| 08-110 | Steel Doors and Frames | M | $191,893.74 | $35,745.58 | $6,008.77 |  | $150,139.39
| 09-510 | Acoustical Ceilings | L | $186,269.37 | $2,403.91 | $37,113.99 |  | $146,751.47
| 09 91 00 | Painting | Material | $71,311.65 | $54,358.01 | $2,495.01 |  | $14,458.63
| 09 91 00 | Painting | Subcontract | $397,650.59 | $162,537.81 | $86,518.63 |  | $148,594.15
| 08-110 | Steel Doors and Frames | Subcontract | $113,218.14 | $30,977.46 | $26,615.51 |  | $55,625.17
| 09.250 | Gypsum Board Assemblies | E | $63,857.60 | $10,289.70 | $20,665.50 |  | $32,902.40
| 09-650 | Resilient Flooring | E | $162,611.92 | $34,701.34 | $12,858.95 | $40,694.12 | $74,357.51
| 08-110 | Steel Doors and Frames | S | $60,586.89 | $24,334.79 | $840.51 |  | $35,411.59
| 09 91 00 | Painting | Labor | $130,759.58 | $98,718.92 | $9,980.84 | $29,476.40 | $-7,416.58
| 12-480 | Entrance Floor Mats | Labor | $158,521.34 | $58,818.74 | $30,912.60 |  | $68,790.00
| 12.480 | Entrance Floor Mats | MAT | $389,800.51 | $227,832.26 | $14,200.27 |  | $147,767.98
| 09-510 | Acoustical Ceilings | O | $59,072.63 | $16,639.78 | $4,340.12 |  | $38,092.73
| 10-280 | Toilet Accessories | Sub | $283,533.10 | $2,492.32 | $5,269.34 |  | $275,771.44
| 10-280 | Toilet Accessories | S | $94,772.92 | $38,785.95 | $13,038.02 |  | $42,948.95
| 09-250 | Gypsum Board Assemblies | Subcontract | $7,108.38 | $4,998.30 | $526.22 |  | $1,583.86
| 09-910 | Painting | Owner | $199,314.06 | $24,070.89 | $11,031.96 | $566.81 | $163,644.40
| 09-250 | Gypsum Board Assemblies | Labor | $60,104.47 | $11,232.28 | $10,379.77 |  | $38,492.42
| 08-110 | Steel Doors and Frames | L | $265,702.63 | $25,056.66 | $71,273.03 | $23,711.00 | $145,661.94
| 12-480 | Entrance Floor Mats | Subcontract | $279,745.67 | $135,534.25 | $54,462.01 |  | $89,749.41
| 12-480 | Entrance Floor Mats | S | $257,042.04 | $154,791.45 | $5,581.62 |  | $96,668.97
| 09-510 | Acoustical Ceilings | O | $168,661.00 | $108,026.69 | $2,652.48 |  | $57,981.83
| 2026-09-30 | Tiling | Owner | $268,273.18 | $194,203.87 | $17,974.23 |  | $56,095.08
| 12-480 | Entrance Floor Mats | E | $445,647.59 | $97,079.60 | $15,750.39 | $37,714.71 | $295,102.89
| 08-110 | Steel Doors and Frames | M | $255,426.77 | $52,431.26 | $79,920.66 |  | $123,074.85
| 09-650 | Resilient Flooring | E | $318,671.93 | $30,656.00 | $78,226.17 | $41,451.07 | $168,338.69
| 10-280 | Toilet Accessories | Sub | $118,446.60 | $34,235.63 | $28,484.57 |  | $55,726.40
| 2026-09-30 | Tiling |  | $359,487.00 | $41,142.84 | $71,644.96 |  | $246,699.20
| 2026-09-30 | Tiling | S | $215,154.23 | $109,637.50 | $22,127.92 |  | $83,388.81
| 09-650 | Resilient Flooring | Owner | $163,166.36 | $28,313.47 | $50,201.59 | $25,485.50 | $59,165.80
| 09-510 | Acoustical Ceilings | S | $355,544.50 | $213,859.73 | $18,584.66 |  | $123,100.11
| 09-510 | Acoustical Ceilings | S | $455,063.25 | $178,746.31 | $3,981.84 |  | $272,335.10
| 09-910 | Painting | Subcontractor | $119,789.11 | $66,164.62 | $486.61 |  | $53,137.88
| 09-910 | Painting | Material | $394,145.31 | $196,637.33 | $56,455.14 |  | $141,052.84
| 2026-09-30 | Tiling | M | $406,202.17 | $41,497.50 | $12,421.72 |  | $352,282.95
| 10-280 | Toilet Accessories | Material | $113,814.42 | $80,556.45 | $3,872.05 |  | $29,385.92
| 08.110 | Steel Doors and Frames | S | $152,413.56 | $75,595.18 | $1,452.15 | $1,778.60 | $73,587.63
| 08-110 | Steel Doors and Frames | L | $243,654.96 | $179,849.15 | $1,166.87 |  | $62,638.94
| 09-910 | Painting | L | $341,404.39 | $240,668.81 | $38,720.99 |  | $62,014.59
| 2026-09-30 | Tiling | Labor | $403,831.75 | $205,366.47 | $64,698.69 |  | $133,766.59
| 09-650 | Resilient Flooring | M | $417,852.72 | $271,454.35 | $35,218.43 |  | $111,179.94
| 09-910 | Painting | Material | $437,469.02 | $4,605.41 | $80,724.94 |  | $352,138.67
| 09-30 | Tiling | S | $197,638.79 | $126,154.46 | $25,316.73 |  | $46,167.60
| 10-280 | Toilet Accessories | LAB | $256,497.67 | $124,229.30 | $35,534.88 |  | $96,733.49
| 10.280 | Toilet Accessories | Material | $333,466.11 | $8,816.61 | $48,363.10 |  | $276,286.40
| 12-480 | Entrance Floor Mats | S | $285,406.11 | $141,313.04 | $25,221.27 |  | $118,871.80
| 10-280 | Toilet Accessories | L | $292,223.68 | $13,510.16 | $105,369.18 | $37,220.83 | $136,123.51
| 09-650 | Resilient Flooring | Material | $36,549.03 | $16,388.08 | $3,569.52 |  | $16,591.43
| 10-280 | Toilet Accessories | E | $302,628.62 | $215,201.78 | $33,092.82 |  | $54,334.02
| 09-650 | Resilient Flooring | S | $302,253.49 | $99,059.19 | $60,791.69 |  | $142,402.61
| 09-650 | Resilient Flooring | S | $288,969.40 | $106,642.36 | $8,409.09 | $10,458.41 | $163,459.54
| 12-480 | Entrance Floor Mats | L | $312,796.35 | $10,849.81 | $14,297.50 |  | $287,649.04
| 10-280 | Toilet Accessories | M | $80,911.90 | $14,596.88 | $25,795.21 |  | $40,519.81
| 09-510 | Acoustical Ceilings | M | $110,220.14 | $12,177.50 | $21,525.21 |  | $76,517.43
| 09-510 | Acoustical Ceilings | LAB | $171,597.68 | $66,333.59 | $42,027.39 |  | $63,236.70
| 09-510 | Acoustical Ceilings | L | $289,214.53 | $166,443.84 | $38,483.23 |  | $84,287.46
| 09-30 | Tiling | Subcontractor | $379,850.38 | $89,930.71 | $53,410.83 | $26,899.95 | $209,608.89
| 09-650 | Resilient Flooring | E | $216,753.94 | $131,350.78 | $8,209.77 |  | $77,193.39
| 09-650 | Resilient Flooring | S | $231,510.01 | $65,628.01 | $23,630.24 |  | $142,251.76
| 09-510 | Acoustical Ceilings | Subcontract | $306,460.31 | $132,227.27 | $4,456.42 |  | $169,776.62
| 09-650 | Resilient Flooring | S | $60,766.61 | $17,464.70 | $3,549.95 |  | $39,751.96
| 08-110 | Steel Doors and Frames | Subcontractor | $445,074.30 | $15,447.05 | $64,665.10 | $16,557.22 | $348,404.93
| 12-480 | Entrance Floor Mats | E | $410,028.79 | $131,513.12 | $8,592.40 | $30,519.69 | $239,403.58
| 09 91 00 | Painting | Subcontract | $432,845.57 | $77,073.18 | $66,594.57 |  | $289,177.82
| 09-30 | Tiling | LAB | $334,154.17 | $198,377.12 | $12,595.82 |  | $123,181.23
| 09-250 | Gypsum Board Assemblies | Labor | $6,130.11 | $1,480.31 | $1,140.19 |  | $3,509.61
| 12-480 | Entrance Floor Mats | S | $336,763.55 | $226,959.25 | $36,441.74 |  | $73,362.56
| 10-280 | Toilet Accessories |  | $400,434.79 | $305,765.75 | $19,680.32 |  | $74,988.72
| 12-480 | Entrance Floor Mats | M | $2,490.78 | $1,575.12 | $353.05 | $9,607.63 | $-9,045.02
| 09-510 | Acoustical Ceilings |  | $118,388.47 | $56,047.68 | $24,731.21 |  | $37,609.58
| 09 29 00 | Gypsum Board Assemblies | O | $154,821.27 | $83,442.74 | $15,602.14 |  | $55,776.39
| 09.650 | Resilient Flooring | L | $75,575.51 | $19,014.96 | $11,665.92 | $33,235.68 | $11,658.95
| 09-910 | Painting | S | $345,191.83 | $64,465.34 | $15,957.84 |  | $264,768.65
| 12-480 | Entrance Floor Mats | Material | $159,188.10 | $74,460.07 | $3,241.80 | $33,229.83 | $48,256.40
| 2026-09-30 | Tiling | Labor | $346,507.52 | $170,718.74 | $18,167.84 |  | $157,620.94
| 09-650 | Resilient Flooring | L | $450,514.97 | $59,484.97 | $46,180.03 |  | $344,849.97
| 09.650 | Resilient Flooring | L | $473,765.93 | $362,870.45 | $30,423.50 | $14,945.59 | $65,526.39
| 09-30 | Tiling | MAT | $8,988.54 | $3,392.38 | $572.47 | $13,474.13 | $-8,450.44
| 09-510 | Acoustical Ceilings | Labor | $209,263.90 | $95,899.15 | $38,740.15 |  | $74,624.60
|  | Interiors Total |  | $29,438,229.81
Mechanical and Electrical | 15-700 | Air Handling Units | M | $8,036.10 | $3,796.49 | $120.70 |  | $4,118.91
| 16-120 | Conductors and Cables | Subcontract | $482,756.89 | $250,824.25 | $35,093.35 |  | $196,839.29
| 16-510 | Interior Lighting | Subcontract | $123,076.52 | $27,622.55 | $23,817.85 | $17,953.10 | $53,683.02
| 16-510 | Interior Lighting | Material | $306,310.62 | $172,473.26 | $20,146.33 |  | $113,691.03
| 16-720 | Fire Alarm | L | $362,104.24 | $3,726.11 | $62,645.05 |  | $295,733.08
| 2026-06-24 | Interior Architectural Woodwork | Labor | $166,746.80 | $9,779.00 | $46,803.25 | $14,095.30 | $96,069.25
| 16-510 | Interior Lighting | Equipment | $222,478.93 | $86,085.32 | $28,166.51 |  | $108,227.10
| 16-720 | Fire Alarm | Material | $128,466.27 | $17,820.58 | $38,063.47 |  | $72,582.22
| 15-400 | Plumbing Fixtures | Labor | $322,464.45 | $114,462.48 | $6,005.83 |  | $201,996.14
| 14-210 | Electric Traction Elevators | E | $177,651.91 | $42,891.33 | $39,276.28 |  | $95,484.30
| 15-400 | Plumbing Fixtures | S | $245,710.59 | $18,218.76 | $70,326.36 |  | $157,165.47
| 14-210 | Electric Traction Elevators | L | $218,677.38 | $58,465.16 | $44,488.37 |  | $115,723.85
| 26 51 00 | Interior Lighting | Material | $64,423.73 | $35,218.19 | $7,596.15 |  | $21,609.39
| 15-820 | Ductwork | S | $94,796.22 | $17,800.46 | $10,942.97 |  | $66,052.79
| 06-24 | Interior Architectural Woodwork |  | $277,597.04 | $71,094.91 | $5,614.33 |  | $200,887.80
| 16-720 | Fire Alarm | M | $74,344.06 | $18,122.03 | $11,066.15 |  | $45,155.88
| 15-820 | Ductwork | Labor | $199,156.20 | $39,456.52 | $38,734.18 |  | $120,965.50
| 15-820 | Ductwork | M | $194,439.63 | $17,050.28 | $7,829.66 |  | $169,559.69
| 2026-06-24 | Interior Architectural Woodwork | S | $377,824.66 | $107,337.99 | $88,770.30 |  | $181,716.37
| 16-510 | Interior Lighting | Subcontract | $284,428.66 | $47,410.09 | $11,180.24 |  | $225,838.33
| 16-120 | Conductors and Cables | L | $334,247.08 | $61,058.78 | $3,234.60 |  | $269,953.70
| 22 11 00 | Plumbing Piping | L | $466,520.19 | $150,688.27 | $21,156.23 |  | $294,675.69
| 16.120 | Conductors and Cables | O | $90,349.47 | $57,486.92 | $5,674.89 | $13,205.75 | $13,981.91
| 15-100 | Plumbing Piping | Material | $117,392.65 | $28,150.21 | $33,597.49 |  | $55,644.95
| 16-720 | Fire Alarm | O | $455,259.21 | $283,436.37 | $53,894.66 |  | $117,928.18
| 15-820 | Ductwork | Sub | $453,090.13 | $185,991.36 | $59,660.63 |  | $207,438.14
| 16-720 | Fire Alarm | Subcontract | $20,952.55 | $14,012.06 | $2,513.53 |  | $4,426.96
| 2026-06-24 | Interior Architectural Woodwork | Labor | $431,704.36 | $234,331.25 | $25,582.38 | $27,699.51 | $144,091.22
| 16-720 | Fire Alarm | S | $423,190.94 | $27,158.25 | $69,408.41 |  | $326,624.28
| 22 11 00 | Plumbing Piping | Equipment | $423,490.77 | $43,319.58 | $12,743.60 |  | $367,427.59
| 16-120 | Conductors and Cables | Material | $304,982.62 | $179,843.56 | $28,322.85 |  | $96,816.21
| 15-820 | Ductwork | S | $129,009.64 | $41,614.41 | $886.15 |  | $86,509.08
| 15-100 | Plumbing Piping | Subcontractor | $353,778.87 | $130,961.61 | $33,073.66 |  | $189,743.60
| 26 51 00 | Interior Lighting | Equipment | $282,519.84 | $61,566.79 | $19,038.01 |  | $201,915.04
| 15-700 | Air Handling Units | Subcontract | $79,199.38 | $53,595.13 | $8,933.92 |  | $16,670.33
| 2026-06-24 | Interior Architectural Woodwork | M | $318,492.21 | $221,884.77 | $32,502.32 |  | $64,105.12
| 15-400 | Plumbing Fixtures | L | $301,737.15 | $2,535.49 | $54,226.44 |  | $244,975.22
| 14-210 | Electric Traction Elevators | S | $352,834.86 | $22,718.17 | $29,723.33 |  | $300,393.36
| 14.210 | Electric Traction Elevators | L | $323,689.50 | $222,734.53 | $4,292.33 |  | $96,662.64
| 14-210 | Electric Traction Elevators | Labor | $212,722.19 | $113,523.93 | $29,517.43 |  | $69,680.83
| 06-24 | Interior Architectural Woodwork | Subcontract | $382,484.08 | $42,892.95 | $62,219.00 |  | $277,372.13
| 15-700 | Air Handling Units | LAB | $324,963.18 | $98,606.38 | $84,354.50 |  | $142,002.30
| 14-210 | Electric Traction Elevators | O | $110,713.00 | $31,419.64 | $23,295.93 |  | $55,997.43
| 16-720 | Fire Alarm | Material | $480,691.83 | $89,649.89 | $56,318.93 |  | $334,723.01
| 16-510 | Interior Lighting | Subcontract | $305,983.85 | $231,010.07 | $27,512.59 |  | $47,461.19
| 15-700 | Air Handling Units | Labor | $62,905.33 | $12,961.24 | $13,513.75 |  | $36,430.34
| 15-400 | Plumbing Fixtures | M | $314,662.88 | $145,443.17 | $12,367.24 | $9,593.55 | $147,258.92
| 2026-06-24 | Interior Architectural Woodwork | Material | $385,269.74 | $137,428.29 | $91,211.43 |  | $156,630.02
| 16-720 | Fire Alarm | Equipment | $469,217.91 | $68,076.26 | $53,713.30 |  | $347,428.35
| 2026-06-24 | Interior Architectural Woodwork | E | $115,454.47 | $3,152.07 | $9,675.88 | $23,827.45 | $78,799.07
| 15-100 | Plumbing Piping | M | $175,172.75 | $98,442.80 | $3,357.26 |  | $73,372.69
| 16-120 | Conductors and Cables | Sub | $34,436.20 | $17,468.93 | $787.44 |  | $16,179.83
| 15-400 | Plumbing Fixtures | E | $437,690.32 | $218,264.82 | $67,741.63 |  | $151,683.87
| 16-120 | Conductors and Cables | Equipment | $399,033.76 | $285,956.02 | $6,367.28 |  | $106,710.46
| 15-400 | Plumbing Fixtures | M | $196,832.64 | $4,885.22 | $25,241.92 |  | $166,705.50
| 16.510 | Interior Lighting | Material | $27,563.03 | $15,944.87 | $651.89 |  | $10,966.27
| 15.400 | Plumbing Fixtures | M | $321,773.92 | $101,619.89 | $50,715.58 | $3,497.57 | $165,940.88
| 14-210 | Electric Traction Elevators | S | $48,997.27 | $33,366.85 | $582.33 |  | $15,048.09
| 16-510 | Interior Lighting | S | $292,674.90 | $52,879.37 | $65,987.46 |  | $173,808.07
| 15-820 | Ductwork | E | $477,291.58 | $213,458.71 | $81,290.04 | $6,795.44 | $175,747.39
| 16-120 | Conductors and Cables | L | $292,138.01 | $173,512.83 | $8,543.17 |  | $110,082.01
| 16-120 | Conductors and Cables | O | $473,848.17 | $166,242.53 | $11,147.70 | $10,441.75 | $286,016.19
| 15-820 | Ductwork | L | $319,845.22 | $131,243.27 | $34,000.04 |  | $154,601.91
| 06-24 | Interior Architectural Woodwork | M | $159,824.37 | $105,490.32 | $14,368.71 |  | $39,965.34
| 15.100 | Plumbing Piping | Material | $446,964.12 | $266,996.04 | $69,419.38 |  | $110,548.70
| 15-400 | Plumbing Fixtures | Subcontract | $96,728.33 | $52,307.71 | $11,739.78 |  | $32,680.84
| 15-400 | Plumbing Fixtures | Subcontract | $427,082.58 | $305,785.11 | $9,260.38 |  | $112,037.09
| 16-120 | Conductors and Cables | Labor | $169,754.72 | $22,292.63 | $6,271.33 |  | $141,190.76
| 16-120 | Conductors and Cables | O | $222,978.38 | $163,358.25 | $3,823.54 |  | $55,796.59
| 16-720 | Fire Alarm | Subcontractor | $340,114.04 | $112,775.42 | $85,068.00 |  | $142,270.62
| 15-820 | Ductwork | MAT | $18,033.08 | $2,010.77 | $4,166.04 | $3,774.69 | $8,081.58
| 2026-06-24 | Interior Architectural Woodwork | Sub | $223,246.99 | $165,388.39 | $19,638.08 |  | $38,220.52
| 2026-06-24 | Interior Architectural Woodwork | MAT | $382,372.70 | $226,356.10 | $58,905.75 |  | $97,110.85
| 2026-06-24 | Interior Architectural Woodwork | E | $451,746.22 | $146,203.07 | $62,445.56 |  | $243,097.59
| 06-24 | Interior Architectural Woodwork | S | $50,104.61 | $19,976.32 | $7,115.17 |  | $23,013.12
| 14-210 | Electric Traction Elevators | Sub | $277,141.93 | $71,512.38 | $6,755.92 |  | $198,873.63
| 16-120 | Conductors and Cables | M | $381,295.83 | $152,837.93 | $14,614.32 |  | $213,843.58
| 2026-06-24 | Interior Architectural Woodwork | S | $345,639.04 | $149,740.24 | $56,446.10 |  | $139,452.70
| 16-510 | Interior Lighting | L | $102,104.66 | $27,933.70 | $23,158.33 |  | $51,012.63
| 2026-06-24 | Interior Architectural Woodwork | Owner | $231,583.32 | $102,108.02 | $38,315.54 |  | $91,159.76
| 22 11 00 | Plumbing Piping | M | $314,128.40 | $211,618.22 | $38,771.32 | $35,962.75 | $27,776.11
| 15-820 | Ductwork | Subcontract | $271,517.77 | $5,999.71 | $100,123.99 |  | $165,394.07
| 16-720 | Fire Alarm | Equipment | $237,550.49 | $65,800.07 | $52,183.51 |  | $119,566.91
| 06-24 | Interior Architectural Woodwork | O | $461,820.73 | $62,023.33 | $114,008.07 |  | $285,789.33
| 16-720 | Fire Alarm | O | $119,492.29 | $90,853.33 | $7,302.77 |  | $21,336.19
| 15-820 | Ductwork | Subcontract | $451,135.09 | $232,091.37 | $33,476.17 | $39,279.69 | $146,287.86
| 14-210 | Electric Traction Elevators | L | $265,617.10 | $41,753.50 | $79,413.04 |  | $144,450.56
| 16-120 | Conductors and Cables | E | $45,710.43 | $34,955.26 | $2,473.99 |  | $8,281.18
| 2026-06-24 | Interior Architectural Woodwork | O | $262,239.91 | $50,440.94 | $49,352.66 |  | $162,446.31
| 15-400 | Plumbing Fixtures | Labor | $11,296.85 | $7,128.05 | $793.53 |  | $3,375.27
| 16-510 | Interior Lighting | Subcontract | $31,669.64 | $22,558.41 | $1,871.72 |  | $7,239.51
| 16-120 | Conductors and Cables | L | $105,846.20 | $9,883.26 | $15,902.12 |  | $80,060.82
| 14-210 | Electric Traction Elevators | Subcontract | $433,915.79 | $76,273.17 | $116,290.16 | $37,754.83 | $203,597.63
| 16-720 | Fire Alarm | Subcontract | $476,410.17 | $333,081.93 | $4,260.67 |  | $139,067.57
| 15-820 | Ductwork | Owner | $60,351.78 | $10,607.51 | $17,695.58 | $33,704.59 | $-1,655.90
| 16-720 | Fire Alarm | Labor | $330,556.71 | $106,176.73 | $77,253.69 |  | $147,126.29
| 15.820 | Ductwork | Labor | $389,558.32 | $13,328.28 | $45,238.72 | $24,201.52 | $306,789.80
| 2026-06-24 | Interior Architectural Woodwork | M | $24,647.48 | $9,618.07 | $2,450.76 |  | $12,578.65
| 2026-06-24 | Interior Architectural Woodwork | S | $60,980.88 | $2,088.27 | $6,230.70 |  | $52,661.91
| 14-210 | Electric Traction Elevators | Equipment | $443,693.54 | $310,789.72 | $12,645.09 |  | $120,258.73
| 15-100 | Plumbing Piping | Prof Services | $364,944.58 | $50,631.71 | $73,253.82 |  | $241,059.05
| 2026-06-24 | Interior Architectural Woodwork | MAT | $410,068.15 | $284,766.53 | $49,973.36 |  | $75,328.26
| 15-820 | Ductwork | M | $440,633.15 | $277,261.03 | $45,608.15 |  | $117,763.97
| 2026-06-24 | Interior Architectural Woodwork | M | $278,127.80 | $24,181.70 | $75,954.48 |  | $177,991.62
| 15-820 | Ductwork | L | $392,677.12 | $102,341.77 | $39,627.21 |  | $250,708.14
| 16-120 | Conductors and Cables | Owner | $80,457.31 | $34,360.08 | $1,121.78 | $29,474.83 | $15,500.62
| 16.510 | Interior Lighting | LAB | $217,611.06 | $154,072.09 | $12,109.64 |  | $51,429.33
| 16-510 | Interior Lighting | Equipment | $219,946.99 | $1,014.01 | $73,084.88 |  | $145,848.10
| 15-400 | Plumbing Fixtures | Labor | $363,139.86 | $7,079.54 | $22,900.89 |  | $333,159.43
| 26 51 00 | Interior Lighting | Labor | $139,215.88 | $107,857.60 | $3,050.00 |  | $28,308.28
| 16-720 | Fire Alarm | S | $214,308.51 | $89,455.66 | $21,117.56 |  | $103,735.29
| 2026-06-24 | Interior Architectural Woodwork | Subcontract | $133,855.08 | $100,555.81 | $6,528.52 |  | $26,770.75
| 16-720 | Fire Alarm | Labor | $105,466.19 | $44,232.04 | $15,453.51 | $734.18 | $45,046.46
| 14-210 | Electric Traction Elevators | Labor | $423,416.91 | $153,392.71 | $67,381.82 |  | $202,642.38
| 15-700 | Air Handling Units | LAB | $134,427.54 | $5,079.75 | $43,666.29 |  | $85,681.50
| 22 11 00 | Plumbing Piping | Labor | $424,336.98 | $106,881.11 | $3,752.72 |  | $313,703.15
| 06-24 | Interior Architectural Woodwork | Material | $320,431.88 | $209,622.18 | $20,209.38 |  | $90,600.32
| 16-120 | Conductors and Cables | E | $402,299.82 | $201,683.51 | $14,453.22 |  | $186,163.09
| 15-820 | Ductwork | E | $63,264.77 | $47,503.21 | $1,117.72 |  | $14,643.84
| 15-700 | Air Handling Units | L | $311,869.88 | $69,637.49 | $2,196.11 |  | $240,036.28
| 15-820 | Ductwork | Labor | $463,151.34 | $174,602.57 | $64,055.49 |  | $224,493.28
| 22 11 00 | Plumbing Piping | Subcontractor | $424,275.60 | $103,210.63 | $99,941.56 |  | $221,123.41
| 2026-06-24 | Interior Architectural Woodwork | L | $188,674.54 | $46,977.95 | $24,932.54 | $24,001.05 | $92,763.00
| 15-400 | Plumbing Fixtures | Material | $190,590.26 | $122,911.94 | $3,450.40 |  | $64,227.92
| 2026-06-24 | Interior Architectural Woodwork | S | $108,743.92 | $332.25 | $27,938.33 |  | $80,473.34
| 15-400 | Plumbing Fixtures | M | $167,661.13 | $5,757.97 | $16,384.96 |  | $145,518.20
|  | Mechanical and Electrical Total |  | $32,764,749.29
Sitework | 02-630 | Storm Drainage | L | $435,241.61 | $266,323.56 | $35,848.33 |  | $133,069.72
| 02.510 | Water Distribution | L | $280,114.19 | $110,920.90 | $30,831.09 |  | $138,362.20
| 17-100 | General Conditions Markup |  | $481,686.94 | $180,656.22 | $6,377.69 |  | $294,653.03
| 02-740 | Asphalt Paving | Sub | $51,211.98 | $37,584.56 | $3,337.12 |  | $10,290.30
| 02-510 | Water Distribution | O | $322,361.31 | $17,710.90 | $102,310.15 |  | $202,340.26
| 02-770 | Curbs and Gutters | Labor | $100,747.34 | $53,512.52 | $14,391.90 |  | $32,842.92
| 32 12 00 | Asphalt Paving | E | $214,003.53 | $9,479.96 | $18,230.07 |  | $186,293.50
| 02-630 | Storm Drainage | L | $371,147.14 | $179,203.31 | $17,453.81 |  | $174,490.02
| 02-770 | Curbs and Gutters | Prof Services | $410,416.04 | $307,957.62 | $20,676.01 |  | $81,782.41
| 02-630 | Storm Drainage | L | $477,535.85 | $263,355.59 | $54,329.50 |  | $159,850.76
| 02-510 | Water Distribution | Sub | $463,304.55 | $42,113.41 | $119,752.00 |  | $301,439.14
| 17-100 | General Conditions Markup | S | $416,743.03 | $201,084.13 | $59,799.18 | $24,961.91 | $130,897.81
| 02-930 | Planting | L | $473,007.61 | $299,739.67 | $56,444.00 |  | $116,823.94
| 17-200 | Contingency | Material | $482,199.77 | $116,919.38 | $67,278.16 |  | $298,002.23
| 17-100 | General Conditions Markup | Material | $192,580.79 | $48,225.23 | $43,537.73 |  | $100,817.83
| 02-630 | Storm Drainage | S | $209,045.86 | $49,375.48 | $49,768.03 |  | $109,902.35
| 02-630 | Storm Drainage | Material | $426,223.63 | $289,655.76 | $18,398.91 |  | $118,168.96
| 02-510 | Water Distribution | L | $45,992.94 | $4,672.02 | $15,739.22 |  | $25,581.70
| 17-200 | Contingency | Labor | $479,495.32 | $246,284.09 | $44,036.33 | $6,850.28 | $182,324.62
| 02-930 | Planting | M | $275,895.87 | $121,189.61 | $51,631.65 |  | $103,074.61
| 17-100 | General Conditions Markup | M | $308,407.09 | $36,373.78 | $2,225.33 | $40,902.85 | $228,905.13
| 02-510 | Water Distribution | Equipment | $343,651.78 | $57,280.04 | $83,060.65 |  | $203,311.09
| 32 12 00 | Asphalt Paving | Labor | $387,952.05 | $128,726.39 | $30,394.89 |  | $228,830.77
| 17-200 | Contingency | L | $388,304.86 | $234,216.94 | $52,825.56 |  | $101,262.36
| 02-930 | Planting | L | $247,499.70 | $89,314.29 | $16,361.35 |  | $141,824.06
| 17-200 | Contingency | S | $391,965.16 | $206,917.21 | $2,007.05 |  | $183,040.90
| 02-630 | Storm Drainage | L | $223,632.40 | $61,034.29 | $40,456.30 | $18,083.49 | $104,058.32
| 02-930 | Planting | Owner | $66,968.25 | $28,888.45 | $826.35 |  | $37,253.45
| 02-740 | Asphalt Paving | S | $11,464.50 | $1,807.97 | $3,389.67 |  | $6,266.86
| 17.100 | General Conditions Markup | LAB | $136,026.92 | $83,597.80 | $11,603.45 |  | $40,825.67
| 02-770 | Curbs and Gutters | Equipment | $182,950.72 | $107,596.46 | $29,300.43 |  | $46,053.83
| 17-100 | General Conditions Markup | M | $417,216.34 | $61,157.81 | $112,527.42 |  | $243,531.11
| 17.100 | General Conditions Markup | E | $351,003.89 | $241,889.87 | $43,533.36 |  | $65,580.66
| 02.630 | Storm Drainage | Subcontract | $367,500.87 | $55,119.50 | $76,691.36 | $17,199.75 | $218,490.26
| 02-930 | Planting | S | $319,105.05 | $158,044.08 | $56,651.41 |  | $104,409.56
| 02-930 | Planting | LAB | $13,307.80 | $2,012.48 | $1,223.22 |  | $10,072.10
| 02-630 | Storm Drainage | Subcontract | $342,377.73 | $88,035.99 | $19,069.66 |  | $235,272.08
| 02-740 | Asphalt Paving | Labor | $324,035.59 | $14,547.96 | $2,145.44 |  | $307,342.19
| 02.930 | Planting | LAB | $192,267.84 | $77,699.60 | $21,832.23 |  | $92,736.01
| 02-630 | Storm Drainage | S | $9,572.12 | $1,747.94 | $3,098.33 | $1,605.60 | $3,120.25
| 02-770 | Curbs and Gutters | Prof Services | $230,390.57 | $42,435.10 | $41,100.51 |  | $146,854.96
| 17-200 | Contingency | L | $429,124.58 | $53,271.14 | $100,484.16 |  | $275,369.28
| 02-770 | Curbs and Gutters | S | $12,702.81 | $1,823.82 | $3,347.35 |  | $7,531.64
| 02-740 | Asphalt Paving | L | $212,207.97 | $40,466.34 | $54,606.91 | $30,889.31 | $86,245.41
| 17-200 | Contingency | Material | $77,100.67 | $16,440.80 | $20,516.44 | $40,562.87 | $-419.44
| 17-100 | General Conditions Markup | LAB | $294,886.49 | $128,015.63 | $31,202.92 |  | $135,667.94
| 02-630 | Storm Drainage | L | $140,406.07 | $49,498.76 | $4,363.25 |  | $86,544.06
| 02.510 | Water Distribution | Subcontract | $409,592.68 | $38,909.01 | $127,814.39 |  | $242,869.28
| 02-930 | Planting | S | $124,809.87 | $34,890.70 | $31,280.30 |  | $58,638.87
| 02-930 | Planting | MAT | $43,754.31 | $1,364.95 | $883.36 |  | $41,506.00
| 02-510 | Water Distribution | Subcontractor | $297,798.42 | $184,752.26 | $38,228.12 |  | $74,818.04
| 02-740 | Asphalt Paving | L | $485,734.03 | $180,072.89 | $108,735.84 | $10,619.32 | $186,305.98
| 02-630 | Storm Drainage | LAB | $323,581.02 | $147,738.53 | $47,931.87 | $33,816.47 | $94,094.15
| 02-930 | Planting | Labor | $127,751.51 | $86,692.41 | $11,878.48 |  | $29,180.62
| 02-630 | Storm Drainage | M | $13,221.54 | $2,473.57 | $871.32 |  | $9,876.65
| 02-510 | Water Distribution | MAT | $60,053.31 | $3,927.01 | $15,276.09 | $34,279.47 | $6,570.74
| 17-200 | Contingency | M | $438,186.67 | $339,884.37 | $8,130.39 |  | $90,171.91
| 02-930 | Planting | M | $414,501.09 | $89,188.62 | $27,902.05 |  | $297,410.42
|  | Sitework Total |  | $15,769,969.57
|  | PROJECT TOTAL |  | $155,679,970.77
Prepared by R. Alvarez, Project Accountant
Values shown are current contract amounts including approved change orders.